## General Road Works
Links to further information
| Traffic Scotland - realtime information on trunk roads including Edinburgh City Bypass |  |  |  | Details of Ward and Locality boundaries
SE Scotland trunk roads maintenance by BEAR Scotland
Key
| Transport for Edinburgh - Lothian Buses and Edinburgh Trams |  |  |  | New or updated information in this version
Underlined entries contain links to maps or further information
Edinburgh Travelling Safely measures and Low Traffic Neighbourhoods
| Our social media channels: |  | X (formerly Twitter) | Facebook | Threads
Excel - use the drop-down arrows to sort by any column. PDF - use CTRL + F to search for any keyword. |  |  |  | NB this is not intended to be a list of all the roadworks in Edinburgh. Please refer to the Scottish Roadworks Register website for basic information on all registered roadworks
Ward | Locality | Street | Location | Contractor / works description | Measures in place | Start | Finish
Almond | North West | GLASGOW ROAD | Between the airport junction and Maybury junction | City of Edinburgh Council - carriageway resurfacing | From 08/11/24 - A8 westbound off- and on-slips at airport junction closed 7.30pm - 6.30am each weekday night for around 3 weeks. Divert to Newbridge and return via A8 (E) for airport access. | 2024-09-16 | 6 weeks estimated
Almond | North West | B9080 | At the M90 bridge | BEAR Scotland - bridge strengthening | Temporary traffic lights. Road closed 10pm - 6am for 4 nights from 23/09/24 with further closures TBA | 2024-09-23 | 2024-12-01
Almond | North West | B9080 | Between Merryhall Farm and the M9 bridge | Scottish Water - new main | Temporary traffic lights | 2024-10-07 | 2024-12-08
Almond | North West | GOTE LANE |  | Scottish Water - waste water repairs | Road closed | 2024-11-11 | TBC
Almond | North West | SILVERKNOWES ROAD - new entry | Between Silverknowes Parkway and Marine Drive | Telecoms company - cherry-picker access to overhead equipment | Road closed 10pm - 5am | 2024-11-22 | 2024-11-23
Almond | North West | HARVEST ROAD | At the rail bridge between Harvest Drive and Norton House | Network Rail - devegetation | Temporary traffic lights 10pm - 8am | 2024-11-23 | 2024-11-24
Almond | North West | QUEENSFERRY AREA |  | Christmas in Queensferry | High Street / Edinburgh Road closed 4pm - 8pm. The Loan closed between High Street and Scotmid car park, 5.45pm - 6pm. | 2024-11-28 | 2024-11-28
Almond | North West | HOPETOUN ROAD | At Stewart Terrace | Comex2000 / Virgin Media - cabling | 4-way temporary traffic lights | 2024-11-29 | 2024-12-03
Almond | North West | MUIRHOUSE PARKWAY | From Pennywell roundabout to (and including) Muirhouse View | Scottish Water - ironwork repairs | Road closed to westbound traffic, Muirhouse View and Pennywell Medway closed at Muirhouse Parkway. | 2024-11-29 | 2024-11-29
Almond | North West | TURNHOUSE ROAD | Between Turnhouse Farm Road and Lennymuir | Telecoms company - cherry-picker access to overhead equipment | Temporary traffic lights | 2024-12-13 | 2024-12-13
Almond | North West | QUEENSFERRY ROAD | At Drum Brae North | Scottish Water - ironwork repair | 3-way temporary traffic lights, no exit from Drum Brae North | 2025-01-10 | 7am 11/01/25
City Centre | South East | CALTON ROAD | Between Waverley station access and New Street | Unsafe rock face, restrictions in place to provide safety zone | Temporary traffic lights. Shuttle system with full-time traffic signals now in operation | 2018-12-01 | Ongoing
City Centre | South East | NORTH BRIDGE |  | City of Edinburgh Council / Balfour Beatty - bridge refurbishment | East footway closed, pedestrian access via west footway. One traffic lane open in each direction (as of 21/04/23) | 2020-02-15 | October 2025
City Centre | South East | TARVIT STREET |  | Redevelopment of King's Theatre | Tarvit Street closed between Home Street and Drumdryan Street. Drumdryan Street northbound only. NCR 75 closed, cycle diversion signed via Valleyfield Street | 2023-02-14 | February 2025 estimated
City Centre | South East | DEVON PLACE | Between West Coates and no. 4 | For Ogilvie Construction | Road closed to southbound traffic. | 2023-06-06 | April 2025
City Centre | South East | MELVILLE STREET | At Walker Street | City of Edinburgh Council - public realm improvements | 3-way temporary traffic lights incorporating the exit from the south leg of Walker Street. North leg of Walker Street closed and no entry to the south leg from Melville Street. | 2024-04-22 | December 2024
City Centre | South East | LAWNMARKET AREA |  | City of Edinburgh Council - road, pavement and drainage improvements, including relaying setts. Click cell for more details. | Phase 1 - Upper Bow closed until December 2024. Phase 2 from 02/12/24. Roundabout junction at Upper Bow / Johnston Terrace closed. Existing Lawnmarket one-way order rescinded to allow access and egress at George IV Bridge. Small vehicle access to Castlehill via Johnston Terrace until 06/01/25, thereafter via Ramsay Lane, | 2024-09-23 | July 2025
City Centre | South East | ROSEBERY CRESCENT | At Haymarket Terrace | Clancy Docwra - urgent sewer investigations / repairs | Road closed | 2024-10-07 | 30/11/24 estimated
City Centre | South East | HAYMARKET TERRACE - road reopened 21/11/24 |  | Clancy Docwra - urgent sewer investigations / repairs on Rosebery Crescent | Road closed to eastbound traffic (access maintained as far as Haymarket Yards). This road will be reopened each weekend in November (5pm Friday - 10pm Sunday) to accommodate rugby traffic. | 2024-10-25 | w/c 18/11/24 estimated
City Centre | South East | KING'S STABLES ROAD | Between Lothian Road and Barrace Steps | For Edinburgh's Christmas | Road closed. Cycle access permitted 24/11/24 - 09/12/24 | 2024-10-28 | 2025-01-17
City Centre | South East | FOUNTAINBRIDGE - work postponed, new dates TBA | At Gardner's Crescent | Scottish Water - hydrant repair | 3-way temporary traffic lights | 2024-11-04 | 15/11/24 TBC
City Centre | South East | GEORGE STREET | Between Charlotte Square and Frederick Street | For Edinburgh's Christmas | Road closed, except for cycles. Loading permitted 6.30am - 9.30am daily: eastbound between Charlotte Square and Castle Street, westbound between Frederick Street and Castle Street. | 2024-11-07 | 2025-01-17
City Centre | South East | CASTLE STREET / NORTH CASTLE STREET | Between Rose Street and just north of George Street | For Edinburgh's Christmas | Roads closed 10am - 11pm daily | 2024-11-08 | 2025-01-17
City Centre | South East | ABBEY MOUNT | Regent Road to Abbeyhill | Wall repairs | Road closed to southbound traffic - will reopen by midnight on Thursday 21/11/24 | 2024-11-11 | 2024-11-22
City Centre | South East | GILMORE PLACE | At Upper Gilmore Place | Scottish Power - new power supply (first phase, further work will be scheduled in the new year) | 3-way temporary traffic lights, Upper Gilmore Place closed | 2024-11-18 | 2024-11-22
City Centre | South East | ST MARY'S STREET - work completed 21/11/24 | At High Street / Jeffrey Street | Clancy Docwra for Scottish Water - urgent sewer repairs | 4-way temporary traffic lights | 2024-11-18 | TBC
City Centre | South East | SHANDWICK PLACE | At Atholl Place | Edinburgh Trams - network maintenance | Road closed to westbound traffic 12am - 4am for 2 mornings | 2024-11-21 | 2024-11-22
City Centre | South East | MORRISON STREET | Semple Street to Gardner's Crescent | Scottish Water - ironwork repair | Road closed to westbound traffic 7pm - 7am | 2024-11-22 | 2024-11-23
City Centre | South East | CANONGATE AREA |  | March | Rolling road closure High Street - Canongate - Abbeyhill - Abbey Mount - Regent Road - Regent Terrace, as required between 1pm and 3pm | 2024-11-23 | 2024-11-23
City Centre | South East | WEST PORT | At King's Stables Road | Verizon - manhole repair | 3-way temporary traffic lights | 2024-11-25 | 2024-11-25
City Centre | South East | PALMERSTON PLACE | At Grosvenor Crescent | Telecoms company - cherry-picker access to overhead equipment | 3-way temporary traffic lights | 2024-11-26 | 2024-11-26
City Centre | South East | HOLYROOD ROAD | At Hammermen's Entry | Scottish Water - network maintenance | 3-way temporary traffic lights | 2024-11-27 | 2024-11-27
City Centre | South East | DUNDAS STREET | At Northumberland Street | Scottish Water - ironwork repair | 4-way temporary traffic lights | 2024-11-27 | 2024-11-27
City Centre | South East | CITY CENTRE & HOLYROOD AREA |  | March - Stand for Peace Rally | Rolling road closure Horse Wynd - Canongate - High Street - Cockburn Street - Market Street - Jeffrey Street - St Mary's Street - Holyrood Road - Holyrood Gait - Queen's Drive - Horse Wynd, as required between 12.30pm and 2pm | 2024-11-30 | 2024-11-30
City Centre | South East | HIGH STREET / LAWNMARKET |  | Event at St Giles' Cathedral | Roads closed 8am - 2pm: High Street / Lawnmarket between George IV Bridge and North Bridge, St Giles' Street, West Parliament Square | 2024-11-30 | 2024-11-30
City Centre | South East | FOUNTAINBRIDGE | At Chalmer's Buildings | Scottish Water - ironwork repair | Stop / Go boards | 2024-12-01 | 2024-12-01
City Centre | South East | MOUND PLACE |  | For Edinburgh's Christmas | Road closed 1pm - 4pm | 2024-12-01 | 2024-12-01
City Centre | South East | GEORGE IV BRIDGE | At Chambers Street | Openreach - manhole repair | 3-way temporary traffic lights | 2025-01-06 | 5 days estimated
City Centre | South East | MEUSE LANE |  | Clancy Docwra for Scottish Water - sewer repairs | Road closed for 5 nights | 2025-01-07 | 2025-01-12
City Centre | South East | YOUNG STREET NORTH LANE |  | SGN - new gas service | Road closed to through traffic at nos 21 - 38 | 2025-01-13 | 2025-01-24
City Centre | South East | HAYMARKET |  | Edinburgh Trams - track maintenance | Clifton Terrace closed westbound, Dalry Road closed citybound. 12.15am - 4.15am | 2025-01-14 | 2025-01-14
City Centre | South East | ST VINCENT STREET |  | Cityfibre - ducting installation | Phase 1 - 4-way temporary traffic lights at Howe Street; Phase 2 - 3-way temporary traffic lights at Cumberland Street with North East Circus Place closed | 2025-01-16 | 2025-01-30
City Centre | South East | BROUGHTON STREET LANE |  | SGN - gas main alteration outside Playfair House | Road closed to through traffic | 2025-01-27 | 2025-02-07
City Centre | South East | CHARLOTTE SQUARE | At George Street | Scottish Water - ironwork repair | 3-way temporary traffic lights | 2025-02-16 | 2025-02-16
City Centre | South East | QUEEN STREET / ALBYN PLACE | At Wemyss Place | Clancy Docwra for Scottish Water | Eastbound inside lane closure | 2025-04-06 | 2025-04-06
Colinton / Fairmilehead | South West | FROGSTON ROAD WEST - not carried out, new date TBA | At Frogston Terrace / Winton Drive | Virgin Media - chamber repair | 3-way temporary traffic lights, Frogston Terrace closed | 2024-11-11 | 2024-11-11
Colinton / Fairmilehead | South West | LANARK ROAD - new entry | At Spylaw Bank Road | BT / KN - manhole repairs | Temporary traffic lights | 2024-11-21 | TBC
Colinton / Fairmilehead | South West | FROGSTON ROAD WEST | At Margaret Rose Drive | BT Morrison - cabling | 3-way temporary traffic lights | 2024-11-25 | 5 days estimated
Colinton / Fairmilehead | South West | WOODHALL ROAD | At Barnshot Road | Scottish Power - cable upgrade | 3-way temporary traffic lights | 2024-11-25 | 2024-11-29
Colinton / Fairmilehead | South West | WOODHALL ROAD | At Barnshot Road | Locktel for Cityfibre - cable, ducting and cabinet installation | 3-way temporary traffic lights | 2024-12-09 | 10 days estimated
Colinton / Fairmilehead | South West | OXGANGS ROAD | Between Swanston Road and New Swanston | BT Circet - pole replacement | Temporary traffic lights | 2025-01-06 | 2025-01-06
Corstorphine / Murrayfield | North West | MURRAYFIELD AREA |  | Scotland Rugby autumn tests: 02/11/24 v Fiji, 10/11/24 v South Africa, 16/11/24 v Portugal, 24/11/24 v Australia | Road closures before and after the match affecting Roseburn, Murrayfield, Haymarket areas plus West Approach Road after the match. Click cell to view a map | 2024-11-02 | 2024-11-24
Corstorphine / Murrayfield | North West | SAUGHTONHALL DRIVE | Between Balgreen Road and Saughtonhall Avenue | Scottish Power / Excalon - proving cable ducts | 2-way temporary traffic lights. Work cleared 16/11/24 for Murrayfield rugby fixture, resumed 17/11/24 | 2024-11-12 | 2024-11-22
Corstorphine / Murrayfield | North West | CORSTORPHINE ROAD | At Western Corner | Scottish Water - manhole repair Date TBC | 4-way temporary traffic lights | 2024-11-23 | 2024-11-23
Corstorphine / Murrayfield | North West | LADYWELL AVENUE | At the rail bridge just off Meadow Place Road | Locktel for Cityfibre - making good temporary reinstatement | Temporary traffic lights | 2024-11-23 | TBC
Corstorphine / Murrayfield | North West | MURRAYFIELD ROAD | At Corstorphine Road | Scottish Power / Excalon - making good the temporary road surface | Road closed | 2024-11-25 | 2024-11-25
Corstorphine / Murrayfield | North West | ST JOHN'S ROAD | At Belgrave Road | Scottish Water - manhole repair | 2-way temporary traffic lights, Belgrave Road and St John's Gardens closed | 2024-11-26 | 2024-11-26
Corstorphine / Murrayfield | North West | CRAIGLEITH CRESCENT | Ravelston Dykes to Queensferry Road | Scottish Power / Excalon - making good the temporary road surface | Rolling programme with temporary traffic lights and side-road closures as required | 2024-11-26 | 2024-12-02
Corstorphine / Murrayfield | North West | KIRK LOAN |  | Corstorphine Christmas lights switch-on | Road closed 5.30pm - 8pm | 2024-11-28 | 2024-11-28
Corstorphine / Murrayfield | North West | ROSEBURN STREET | At the tram bridge | Edinburgh Trams - bridge maintenance | Off-peak temporary traffic lights. | 2024-12-09 | 2024-12-13
Craigentinny/ Duddingston | North East | RESTALRIG ROAD | At Alemoor Park | Telecoms company - pole installation | 3-way temporary traffic lights 10am - 4pm each day | 2024-11-18 | 2024-11-20
Craigentinny/ Duddingston | North East | PORTOBELLO ROAD / MOIRA TERRACE | At Craigentinny Avenue and Craigentinny Crescent in turn | Cityfibre - snagging works | Temporary traffic lights | 2024-11-22 | 2024-11-25
Craigentinny/ Duddingston | North East | PIERSFIELD TERRACE | Between Northfield Broadway and Craigentinny Avenue | Scottish Water - network maintenance | Temporary traffic lights | 2024-12-04 | 2024-12-08
Craigentinny/ Duddingston | North East | RESTALRIG CRESCENT |  | Clancy Docwra for Scottish Water | Road closed to through traffic between no. 17 and no. 42 | 2025-01-06 | 2025-01-14
Drum Brae / Gyle | North West | CLERMISTON ROAD NORTH |  | Scottish Power - street lighting repairs | Temporary traffic lights Narrow lanes | 2024-11-14 | 27/11/24 estimated
Drum Brae / Gyle | North West | GLASGOW ROAD | Between Maybury Road and Gogar roundabout | Scottish Power - cable fault | Westbound inside lane closed outside B&M | 2024-11-18 | TBC
Drum Brae / Gyle | North West | DRUM BRAE SOUTH | At Templeland Road | Scottish Water - ironwork repair | Temporary traffic lights, side roads closed | 2024-12-05 | 2024-12-05
Drum Brae / Gyle | North West | DRUM BRAE SOUTH | Between Glasgow Road and Corstorphine Bank Terrace | Clancy Docwra for Scottish Water - pipe renewal | Northbound lane closure and contraflow | 2025-01-27 | 2025-02-02
Forth | North West | FERRY ROAD AVENUE |  | City of Edinburgh Council - carriageway resurfacing | Road closed (weekdays only) | 2024-11-06 | 2024-11-22
Forth | North West | BOSWALL GARDENS |  | Scottish Water - mains upgrade | Road closed at Boswall Terrace 8am - 5pm each day | 2024-11-18 | 6 weeks estimated
Forth | North West | LOWER GRANTON ROAD | Around 100m east of Wardie Square | Scottish Water - manhole construction | 3-way temporary traffic lights, bus stops closed in the works area | 2024-12-02 | 2024-12-06
Forth | North West | PILTON PLACE | Between Pilton Loan and Boswall Parkwsay | Clancy Docwra for Scottish Water | Road closed | 2025-04-07 | 2025-04-13
Fountainbridge/ Craiglockhart | South West | CRAIGLOCKHART AVENUE AREA |  | SGN - gas main renewal (click cell for more information) | Craiglockhart Avenue closed to northbound traffic from 26/10/24 for approximately 4 weeks (temporary traffic lights at Lanark Road removed 11/11/24). Next phase - 4-way temporary traffic lights at Craiglockhart crossroads. | 2024-10-14 | March 2025
Fountainbridge/ Craiglockhart | South West | DUNDEE STREET | At Fountain Park | Telecoms company - cell site preparations (resumption of work started on 04/11/24) | Off-peak 2-way temporary traffic lights | 2024-11-17 | 2024-11-21
Fountainbridge/ Craiglockhart | South West | CHESSER AVENUE | At Hutchison Road / New Mart Road | Virgin Media - ducting installation | 4-way temporary traffic lights | 2024-11-18 | 2024-11-22
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD - not carried out | At Coxfield | Scottish Water - ironwork repair | 3-way temporary traffic lights | 2024-11-20 | 2024-11-20
Fountainbridge/ Craiglockhart | South West | HUTCHISON CROSSWAY | Between Slateford Road and PDSA | Scottish Power / Excalon - proving cable ducts | Road closed | 2024-11-21 | 2024-12-11
Fountainbridge/ Craiglockhart | South West | DUNDEE STREET | At Fountain Park | Telecoms company - pole installation | Off-peak temporary traffic lights. | 2024-11-25 | 2024-11-29
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | At Chesser Avenue | Scottish Power - street lighting repairs | 3-way temporary traffic lights | 2024-11-25 | 2024-11-29
Fountainbridge/ Craiglockhart | South West | SLATEFORD ROAD | At Chesser Avenue | Network Rail - bridge inspection | 3-way temporary traffic lights 10pm - 6am | 2024-12-13 | 2024-12-14
Fountainbridge/ Craiglockhart | South West | COLINTON ROAD | At Craiglockhart Road North | Clarke Telecom - site investigations | 2-way temporary traffic lights | 2024-12-16 | 2024-12-17
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | Chesser Avenue to Elfin Square | Scottish Power - cable jointing | Citybound inside / bus lane closed | 2025-01-06 | 2025-01-27
Fountainbridge/ Craiglockhart | South West | LANARK ROAD | Craiglockhart Avenue to Water of Leith visitor centre | Scottish Power - street lighting repairs | Westbound insde lane closed, temporary stop for westbound buses | 2025-01-07 | 2025-01-11
Fountainbridge/ Craiglockhart | South West | ASHLEY TERRACE | Between Shandon Street and Shaftesbury Park | Clancy Docwra for Scottish Water | 2-way temporary traffic lights | 2025-01-08 | 2025-01-10
Fountainbridge/ Craiglockhart | South West | ASHLEY TERRACE | At Cowan Road | Comex2000 for Virgin Media | 3-way temporary traffic lights | 2025-01-14 | 2025-01-16
Fountainbridge/ Craiglockhart | South West | ANGLE PARK TERRACE | At Slateford Road / Ardmillan Terrace | Clancy Docwra for Scottish Water | 4-way temporary traffic lights | 2025-02-03 | 2025-02-11
Fountainbridge/ Craiglockhart | South West | COLINTON ROAD | At Craiglockhart Park | Scottish Water - manhole repair | 2-way temporary traffic lights, Craiglockhart Park closed | 2025-02-27 | 2025-02-27
Inverleith | North West | CANON STREET |  | Building development | Road closed | 2023-04-17 | End of 2024 estimated
Inverleith | North West | INVERLEITH PLACE | Between Arboretum Place / Arboretum Road and Inverleith Row | SGN - gas main renewal | 4-way temporary traffic lights at Arboretum Road roundabout for around 2 weeks then working eastwards with 2/3-way temporary traffic lights | 2024-08-13 | November 2024
Inverleith | North West | DEANHAUGH STREET | At Leslie Place | City of Edinburgh Council - junction upgrade (resurfacing, footway widening and new pedestrian crossing) | Temporary traffic lights, Leslie Place closed | 2024-10-28 | 5 weeks estimated
Inverleith | North West | FERRY ROAD | At Pilton Drive | Scottish Power - cable jointing Postponed until January | Temporary traffic lights | 2024-11-08 | 2024-11-27
Inverleith | North West | HILLPARK AVENUE |  | Clancy Docwra for Scottish Water - sewer repairs | Road closed to through traffic at no. 30 (north east corner) | 2024-11-18 | 2024-12-02
Inverleith | North West | INVERLEITH ROW | At Inverleith Place | Telecoms company - new cell site | 2-way temporary traffic lights, Inverleith Place closed. 9pm - 5am for 3 nights | 2024-11-18 | 2024-11-21
Inverleith | North West | GLENOGLE ROAD | At rear of Tanfield | Scottish Power - cable fault | Temporary traffic lights proposed | 2024-11-19 | TBC
Inverleith | North West | COMELY BANK ROAD | At Fettes Avenue | Scottish Water - repairs to burst pipe | 3-way temporary traffic lights, Learmonth Avenue closed | 2024-11-20 | TBC
Inverleith | North West | RAVELSTON DYKES ROAD - not carried out | At Craigcrook Road | BT / KN - manhole repairs Date TBC | 4-way temporary traffic lights | 2024-11-20 | 2024-11-20
Inverleith | North West | INVERLEITH ROW - work extended for a 2nd night | At Brandon Terrace | Hillhouse / City of Edinburgh Council - snagging works | Temporary traffic lights 7pm - 6am | 2024-11-20 | 21/11/24 22/11/24
Inverleith | North West | TELFORD ROAD | At Groathill Avenue | Scottish Power / Excalon - carriageway resurfacing | 3-way temporary traffic lights (incorporating McDonalds car park exit), Groathill Avenue and Groathill Road South closed | 2024-11-29 | 2024-12-01
Inverleith | North West | INVERLEITH ROW | At Inverleith Place | Telecoms company - new cell site (pole installation) | 2-way temporary traffic lights, Inverleith Place closed. 9pm - 5am for 3 nights | 2025-01-09 | 2025-01-12
Inverleith | North West | DAVIDSON ROAD | Between Crewe Road South and Davidson Park | Clancy Docwra for Scottish Water | Road closed | 2025-01-15 | 2025-01-22
Leith | North East | LINDSAY ROAD BRIDGE | Pedestrian / cycle bridge between Nicholfield and Lindsay Road main carriageway | City of Edinburgh Council - public safety measure | Bridge closed, pedestrian and cycle diversion as signed. Hawthornvale Path beneath remains open | 2021-12-15 | Until further notice
Leith | North East | LOCHEND ROAD | Between Vanburgh Place and Hermitage Park Grove | City of Edinburgh Council - footway resurfacing | 2-way temporary traffic lights | 2024-10-03 | February 2025 estimated
Leith | North East | MARITIME STREET | Between Queen Charlotte Street and Maritime Lane | Subsidence investigation | Road closed | 2024-10-10 | TBC
Leith | North East | SUMMERFIELD PLACE | At East Hermitage Place | Scottish Power - mains renewal | Road closed | 2024-11-04 | 2025-01-26
Leith | North East | GREAT JUNCTION STREET | Between Foot of the Walk and Henderson Street | City of Edinburgh Council - construction of segregated cycle lane | Lane closures and contraflow | 2024-11-18 | Summer 2025
Leith | North East | LINKS PLACE | At Salamander Place | Comex2000 / Virgin Media - manhole repair | 3-way temporary traffic lights | 2024-12-02 | 2024-12-03
Leith | North East | HENDERSON STREET | Between Great Junction Street and Yardheads | City of Edinburgh Council - construction of segregated cycle lane | Lane closures, parking restrictions, temporary traffic lights if required. A one-way (southbound) system will be installed with northbound access via Vables Wynd, exact dates for this remain TBC. | 2024-12-03 | Spring 2025
Leith | North East | NORTH JUNCTION STREET | At Lindsay Road | Clancy Docwra for Scottish Water | Northbound inside lane closed at the junction (off-peak hours only) | 2025-01-05 | 2025-01-06
Leith Walk | North East | BRUNSWICK STREET | At Leith Walk | Safety measure | Road closed | 2022-08-24 | Until further notice
Leith Walk | North East | BROUGHTON ROAD | Between McDonald Road and North Pilrig Heights | Water main connection at Powderhall development site | Temporary traffic lights | 2024-10-28 | 15/11/24 estimated 22/11/24
Leith Walk | North East | HAWKHILL AVENUE | At Albion Place | Scottish Power - cable fault | Temporary traffic lights | 2024-11-11 | TBC
Leith Walk | North East | BONNINGTON ROAD | Outside Parkside primary school | Scottish Water - meter renewal To be replanned for January | Temporary traffic lights | 2024-11-15 | 2024-11-15
Leith Walk | North East | EASTER ROAD | At Albion Road | Scottish Water - manhole repair To be done in conjunction with Easter Road work on 23/11/24 | 3-way temporary traffic lights 7pm - 7am | 2024-11-15 | 2024-11-16
Leith Walk | North East | BONNINGTON ROAD - work postponed | Between Burlington Street and Anderson Place | BT Morrison - cabling | Overnight temporary traffic lights (8pm - 6am) | 2024-11-18 | 2024-11-22
Leith Walk | North East | EASTER ROAD | Between Brunswick Road and Albion Road | Scottish Water - pipe repairs | 2-way temporary traffic lights. Albion Road and Brunswick Road closed | 2024-11-23 | 2024-11-24
Leith Walk | North East | BONNINGTON ROAD | At Anderson Place | Drainage connections at development site | 3-way temporary traffic lights, Anderson Place closed | 2024-11-25 | 2-3 weeks estimated
Leith Walk | North East | EASTER ROAD AREA |  | Hibs v Aberdeen, kick-off 3pm | Roads closed before and after the match: Hawkhill Avenue / Close, St Clair Street, Albion Place / Road / Terrace / Gardens, Harrismith Place. Local parking restrictions as signed | 2024-11-26 | 2024-11-26
Leith Walk | North East | PILRIG GARDENS | At no. 19 | Clancy Docwra for Scottish Water | Road closed to through traffic | 2024-11-27 | 7 days estimated
Leith Walk | North East | EASTER ROAD AREA |  | Scotland v Finland (Women's Euro 2025 qualifying match), kick-off 7.35pm | Roads closed before and after the match: Hawkhill Avenue / Close, St Clair Street, Albion Place / Road / Terrace / Gardens, Harrismith Place. Local parking restrictions as signed | 2024-11-29 | 2024-11-29
Leith Walk | North East | EASTER ROAD AREA |  | Hibs v Ross County, kick-off 3pm | Roads closed before and after the match: Hawkhill Avenue / Close, St Clair Street, Albion Place / Road / Terrace / Gardens, Harrismith Place. Local parking restrictions as signed | 2024-12-14 | 2024-12-14
Leith Walk | North East | ANNANDALE STREET | At East London Street | Cityfibre | 4-way temporary traffic lights, East London Street closed | 2025-01-06 | 5 days estimated
Liberton / Gilmerton | South East | MAYFIELD ROAD - all work finished | From Liberton Road for around 150m | Development site compound / loading area | Road closed to northbound traffic, diversion signed via Liberton Road - Esslemont Road. Road closed in both directions 15-19/11/24 for final resurfacing. ROAD OPEN IN BOTH DIRECTIONS AS OF 19/11/24 | 2022-01-10 | December 2024
Liberton / Gilmerton | South East | LASSWADE ROAD / KIRK BRAE | Between Captain's Road and Claverhouse Drive | City of Edinburgh Council - carriageway resurfacing, new pavement build-outs and protected cycle lanes. Click cell for more details. | Surfacing work largely complete. Installation of cycle lanes starts w/c 04/11/24 with lane closures and temporary traffic lights as required. | 2024-07-29 | 15 weeks estimated
Liberton / Gilmerton | South East | WALTER SCOTT AVENUE |  | City of Edinburgh Council - footway resurfacing | Road closed in sections | 2024-07-29 | 2024-11-22
Liberton / Gilmerton | South East | GILMERTON ROAD | At Burdiehouse Burn (between Moredunvale Road and Ellen's Glen Road) | Scottish Power - trial holes | Temporary traffic lights | 2024-11-18 | 2024-11-22
Liberton / Gilmerton | South East | OLD DALKEITH ROAD | Between Walter Scott Avenue and Kingston Avenue | City of Edinburgh Council - tree trimming | Off-peak temporary traffic lights. | 2024-11-19 | 2024-11-21
Liberton / Gilmerton | South East | MOREDUNVALE ROAD - new entry | Between Gilmerton Road and (and including) Moredunvale Grove | City of Edinburgh Council - ironwork repairs | Road closed 7pm - 6am | 2024-11-21 | 2024-11-22
Liberton / Gilmerton | South East | GILMERTON ROAD | At Robin's Nest | Scottish Power - trial holes | 4-way temporary traffic lights | 2024-11-22 | 2024-11-23
Liberton / Gilmerton | South East | GILMERTON DYKES STREET | At Moredun Dykes Road | Cityfibre - road repairs | Temporary traffic lights | 2024-11-23 | 2024-11-23
Liberton / Gilmerton | South East | LASSWADE ROAD | At The Murrays | Telecoms company - cherry-picker access to overhead equipment | 3-way temporary traffic lights | 2024-11-30 | 2024-12-01
Liberton / Gilmerton | South East | GILMERTON ROAD | At Guardwell Glen | Telecoms company - trial holes for new pole | 3-way temporary traffic lights | 2024-12-08 | 2024-12-08
Midlothian |  | OLD CRAIGHALL ROAD | Between Newton Cottages and Millerhill | Carriageway realignment, drainage and service installations | Temporary traffic lights | 2024-09-02 | End of 2024 estimated
Morningside | South East | MARCHMONT CRESCENT | South section between Warrender Park Road and Marchmont Road | Scottish Water - improvements to waste water network (click cell for more information) | Work here resumed 07/07/24 with lane and parking restrictions as signed. Road closed from 12/08/24 | 2022-11-07 | End of 2024 estimated
Morningside | South East | PITSLIGO ROAD |  | Scottish Power - trial holes | Temporary traffic lights | 2024-11-15 | 18/11/24 28/11/24
Morningside | South East | GREENBANK CRESCENT | Between Greenbank Loan and Greenbank Road | Clancy Docwra for Scottish Water | 2-way temporary traffic lights | 2024-11-18 | 2024-11-26
Morningside | South East | GREENHILL PARK | At Morningside Road | Scottish Power - mains upgrade | Road closed | 2024-11-18 | 2024-11-22
Morningside | South East | MYRESIDE ROAD | At Myreside Court | BT Circet - manhole repair | 3-way temporary traffic lights | 2024-11-23 | 2024-11-24
Morningside | South East | VIEWFORTH - work postponed | At the canal bridge | Clancy Docwra for Scottish Water - sewer repairs | Road closed | 2024-11-23 | 2024-11-23
Morningside | South East | BRUNTSFIELD PLACE | At Viewforth | Clancy Docwra for Scottish Water | 2-way temporary traffic lights, Viewforth closed | 2025-01-08 | 2025-01-14
Pentland Hills | South West | LANARK ROAD WEST - works update | At Bridge Road | City of Edinburgh Council - junction upgrade | Temporary traffic lights. Main traffic lights back in operation 20/11/24. Final surfacing and line marking will be done when the weather is warmer. | 2024-10-14 | 2024-11-22
Pentland Hills | South West | BLINKBONNY ROAD | At the s-bends above Kinleith mill | City of Edinburgh Council - collapsed gully | Temporary traffic lights | 2024-11-12 | TBC
Pentland Hills | South West | GLENBROOK ROAD | Just west of Glenbrook village | Scottish Water - repairs to burst pipe | Road closed | 2024-11-15 | TBC
Pentland Hills | South West | ADDISTON FARM ROAD |  | City of Edinburgh Council - carriageway resurfacing | Road closed | 2024-11-17 | 2024-11-21
Pentland Hills | South West | MURRAYBURN DRIVE | At Wester Hailes School | Utility installations | Temporary traffic lights | 2024-11-18 | 2024-12-01
Pentland Hills | South West | BABERTON AVENUE | North of Juniper Park Avenue | Christmas lights switch-on | Road closed 4pm - 6pm | 2024-11-24 | 2024-11-24
Pentland Hills | South West | A71 | At Hatton Mains | Scottish Water - tank emptying | Temporary traffic lights 10am - midday approximately | 2024-11-27 | 2024-11-27
Portobello/ Craigmillar | North East | BRUNSTANE ROAD | Between Milton Road East and Argyle Crescent / Dalkeith Street | City of Edinburgh Council - Low Traffic Neighbourhood trial Click cell for more details | Road closed to through traffic, except cycles | 2022-02-15 | Ongoing
Portobello/ Craigmillar | North East | BELLFIELD STREET | Between Straiton Place and the Promenade | For roof repairs at Portobello Baths | Road closed | 2024-07-15 | 31/01/25 estimated
Portobello/ Craigmillar | North East | NEWCRAIGHALL ROAD / NIDDRIE MAINS ROAD | Between Whitehill Road and Hay Avenue | City of Edinburgh Council - carriageway resurfacing | Temporary traffic lights and side-road closures as required, 7.30pm - 6am. Some daytime lane restrictions for gully and traffic signals works. 4-way temporary traffic lights at The Wisp crossroads each weekday night from 06/11/24 until 22/11/24 | 2024-09-09 | 10 weeks estimated
Portobello/ Craigmillar | North East | BRUNSTANE TO NEWCRAIGHALL CYCLE PATH | Section between Newcraighall Road and Bauld Drive | Advance Construction - service diversions | Path closed | 2024-10-28 | 2025-02-28
Portobello/ Craigmillar | North East | BRUNSTANE ROAD | Various locations between Joppa Road and Milton Road | GTC Pipelines - utility connections for housing development | Temporary traffic lights | 2024-10-28 | March 2025
Portobello/ Craigmillar | North East | ARGYLE CRESCENT |  | Power cable installation for development site | Temporary traffic lights | 2024-11-12 | 2024-12-10
Portobello/ Craigmillar | North East | DUDDINGSTON PARK SOUTH | Between The Wisp crossroads and Cleekim Drive | Scottish Water - urgent works to repair burst pipe | Temporary traffic lights | 2024-11-21 | 1-2 days
Portobello/ Craigmillar | North East | SEAFIELD ROAD EAST | At King's Road junction | Scottish Water - manhole repair | Lane closures on Seafield Road East, Portobello Road and Portobello High Street approaches, King's Road closed except for left turn into Portobello High Street | 2024-11-21 | 7am 22/11/24
Portobello/ Craigmillar | North East | BAILEYFIELD ROAD | At Sir Harry Lauder Road | Network Rail - devegetation at the rail bridge | Road closed 10pm - 6am | 2024-11-23 | 2024-11-24
Sighthill/Gorgie | South West | GORGIE ROAD | At Stewart Terrace | SGN - gas leak repairs | 2-way temporary traffic lights, Stewart Terrace closed | 2024-11-01 | TBC
Sighthill/Gorgie | South West | PARKHEAD TERRACE | At Parkhead Loan | Scottish Power - new substation | Temporary traffic lights | 2024-11-04 | 2024-12-13
Sighthill/Gorgie | South West | MCLEOD STREET / RUSSELL ROAD | From the side of Tynecastle high school to Sauchiebank | Energy Assets - power cable installation | McLeod Street closed from 11/11/24 until work reaches the school car park then temporary traffic lights. Restrictions to be cleared for match days at Tynecastle. | 2024-11-11 | End of December estimated
Sighthill/Gorgie | South West | DALRY ROAD | At West Approach Road | Balfour Beatty / City of Edinburgh Council - bridge works for Roseburn to Union Canal project | Temporary traffic lights 7.30pm - 6am each night | 2024-11-11 | 2024-11-26
Sighthill/Gorgie | South West | WEST APPROACH ROAD | At Dundee Street | Balfour Beatty / City of Edinburgh Council - toucan crossing installation for Roseburn to Union Canal project | Westbound lane closure | 2024-11-11 | 2024-11-22
Sighthill/Gorgie | South West | BALGREEN ROAD | Between Gorgie Road and Stevenson Road | Scottish Power / Excalon - proving cable ducts | Lane closures and contraflow (restrictions cleared over weekend of 23-24/11/24) | 2024-11-17 | w/c 25/11/24 estimated
Sighthill/Gorgie | South West | LONGSTONE ROAD - new entry | Between Kingsknowe Road North and Redhall Avenue | Scottish Water - manhole repairs | Temporary traffic lights | 2024-11-21 | TBC
Sighthill/Gorgie | South West | WEST APPROACH ROAD | At Dundee Street | Balfour Beatty / City of Edinburgh Council - toucan crossing installation for Roseburn to Union Canal project | Eastbound lane closure, on-ramp from Dundee Street closed. No restrictions 24/11/24 to accommodate rugby diversions. | 2024-11-21 | 2024-11-28
Sighthill/Gorgie | South West | GORGIE AREA |  | Hearts v Celtic, kick-off 7.45pm | McLeod Street, Wheatfield Street, Wheatfield Place, Russell Road and Murieston Crescent closed before and after the match, Gorgie area parking restrictions as signed | 2024-11-23 | 2024-11-23
Sighthill/Gorgie | South West | GORGIE AREA |  | Hearts v Aberdeen, kick-off 3pm | McLeod Street, Wheatfield Street and Wheatfield Place closed before and after the match, Gorgie area parking restrictions as signed | 2024-12-01 | 2024-12-01
Sighthill/Gorgie | South West | GORGIE ROAD | At McLeod Street | Network Rail - bridge works | Temporary traffic lights 10pm - 6am for 4 nights | 2024-12-02 | 2024-12-06
Sighthill/Gorgie | South West | ROBERTSON AVENUE | Between Gorgie Road and Sinclair Place | BT Circet - ducting installation | Road closed | 2025-01-06 | 2025-01-13
Sighthill/Gorgie | South West | STENHOUSE STREET WEST | Between Saughton Mains Street and Saughton Mains Bank | Clancy Docwra for Scottish Water - pipe renewal | Road closed | 2025-01-17 | 2025-01-20
Sighthill/Gorgie | South West | BANKHEAD CROSSWAY NORTH | Between Bankhead Drive and Bankhead Broadway | Scottish Water - ironwork repair | Temporary traffic lights | 2025-01-19 | 2025-01-19
Sighthill/Gorgie | South West | SLATEFORD ROAD | At Primrose Terrace | Clancy Docwra for Scottish Water | 2-way temporary traffic lights | 2025-01-27 | 2025-01-28
Southside / Newington | South East | SYLVAN PLACE | At Rillbank Crescent | Building development | Road closed | 2023-09-27 | March 2025
Southside / Newington | South East | HOPE TERRACE - start delayed, new dates TBA | At Whitehouse Loan | Scottish Power - cable jointing | 3-way temporary traffic lights | 2024-09-24 | 2024-10-07
Southside / Newington | South East | MACDOWALL ROAD | West side of its junction with Savile Place | Clancy Docwra for Scottish Water | Road closed | 2024-11-18 | 2024-11-24
Southside / Newington | South East | BLACKFORD AVENUE | Between Mortonhall Road and South Oswald Road | BT Circet - manhole repair | Road closed | 2024-11-24 | 2024-11-24
Southside / Newington | South East | NEWINGTON ROAD | At East / West Preston Street | Openreach - service installation | 4-way temporary traffic lights | 2024-11-24 | 2024-11-24
Southside / Newington | South East | BLACKBARONY ROAD |  | Scottish Power - trial holes | 2-way temporary traffic lights | 2024-11-25 | 2024-11-29
Southside / Newington | South East | PARKSIDE TERRACE | At Dalkeith Road | City of Edinburgh Council - carriageway resurfacing | Road closed | 2024-11-25 | 2024-11-29
Southside / Newington | South East | WEST MAYFIELD | At Minto Street / Mayfield Road | Clancy Docwra for Scootsih Water - lead replacement | Road closed | 2024-11-25 | 29/11/24 estimated
Southside / Newington | South East | SOUTH LAUDER ROAD |  | Scottish Power - trial holes | Temporary traffic lights | 2024-11-26 | 2024-11-30
Southside / Newington | South East | RELUGAS ROAD | Between Mayfield Road and Findhorn Place | Scottish Power - trial holes | 2-way temporary traffic lights | 2024-11-28 | 2024-12-02
Southside / Newington | South East | MAYFIELD ROAD | At West Mains Road / Esslemont Road | Clancy Docwra for Scottish Water | 4-way temporary traffic lights | 2025-01-13 | 2025-01-18
Southside / Newington | South East | GILMERTON ROAD | At Orrok Park | Scottish Water - manhole repair | 3-way temporary traffic lights | 2025-01-19 | 2025-01-19
Southside / Newington | South East | RATCLIFFE TERRACE | Between Fountainhall Road and Grange Loan | Clancy Docwra for Scottish Water | Lane closures / contraflow | 2025-01-27 | 2025-02-02
Trunk road network |  | M90 | At B9080 Kirkliston | BEAR Scotland - bridge strengthening | Southbound lane closures approaching M9 J1a. Road closed to southbound traffic 8pm - 6am on the night of 23/09/24 with further closures TBA | 2024-09-23 | December 2024
Trunk road network |  | M8 | At J2 Claylands | BEAR Scotland - bridge works | Westbound off-slip to M9 closed 8pm - 6am each night | 2024-11-25 | 2024-12-07
Trunk road network |  | A702 | At A703 | BEAR Scotland - preparatory work for installation of signalised junction | A702 closed, 7.30pm - 6am each weekday night | 2024-12-02 | 2024-12-14
Trunk road network |  | M9 | J1A - J2 | BEAR Scotland - carriageway resurfacing after J1B | Road closed to north / westbound traffic 7.30pm - 6am for 8 nights (excluding Saturday and Sunday) | 2024-12-02 | 2024-12-12
Roadworks & events report
Effective from 21 November 2024